## Peoject-List
SNO | Project Name | Line of Business | Project Manager (IT) | Description | Business Benefit | Project Phase | Project Start Date | Planned End Date | Revised End Date | Schedule RAG Status | Remarks
1 | ELT Booking | Reservations | Satyam Prajapati | Make the ELT process automated along with SSR included with PNR cancellation. | - Reduction of manual intervention in ELT bookings. | UAT | Oct, 2017 | 2018-02-21 | TBD | Behind | Working on Multicity Booking
[5 empty] | - Process efficiency. |  | May, 2018 |  |  |  | Updated Report on Admin Pandel (UAT)
- Visibility to user while booking under ELT
Provision to updated Meal (UAT)
- Bugs have been reported by the reservations team related to the timings for international flights.Development team is working on fixing this bug.
2 | SOD OAT (Other Airline Ticketing) | Travel Desk | Satyam Prajapati | - Other Airline ticketing (OAT) module will capture Spicejet’s Employee Flight (NON-SpiceJet Airline) and Hotel booking requests (Contractual and Non-Contractual Hotel) | - Operational Efficiency | Development | Jan, 2018 | TBD | TBD | On Track | Working on to manage ITH document as suggested Flight Price & variance
[5 empty] | - This automation will overcome the manual hotel booking and approval. |  | March, 2018
[5 empty] | - Reduce system abuse. |  | March, 2019
- Notification of bookings will be automated.
3 | SOD ZOHO Expense Integrations | Finance, HR | Satyam Prajapati | Zoho Expense Integration with SOD application. | - Facilitate the employee to create trips on ZOHO Expense. | UAT | 2018-09-24 | 2019-03-29 | 2019-03-29 | On Track | NA
[5 empty] | - Each trip created becomes a unique ID against which all non-CTC expenses are claimed, thus better view of all expenses for both Finance Team and the employee. |  |  |  | 2019-03-31
4 | SOD Feedback Level1 -Pahse 2 | Marketing,SSQ | Satyam Prajapati | Provision to capture SOD feedback via Email and reports for data analysis | Facilitate feedback collection from SOD travelers in a simple manner | Go Live | 2019-02-12 | 2019-03-10 | 2019-03-12 | On Track | NA
5 | SOD- Employee Change Request Management | Admin,HR | Satyam Prajapati | Provision to send request with HR/Finance Team for correction in personal information and changes in HOD | - Reduce manual intervention of sharing email ID and mobile no. before processing a booking. | Testing | 2018-09-24 | 2018-12-31 | 2019-04-30 | Behind | NA
- Better user experience.
6 | SOD - Hotel Integration | Travel Desk | Satyam Prajapati | SOD/NON-SOD Booking automation for SpiceJet Employees/Vendors. | This automation will overcome the manual hotel booking and approval. | Go Live | 2016-03-01 | 2016-09-30 | 2018-12-31 | On Track | Auto system generated approval reminder for HOD --On going
[5 empty] | - Reduce misuse of the system. |  |  | 2018-12-31 |  |  | Auto system generated approval reminder for NON-Contractual hotel financial approval.--On going
- Notification of bookings will be automated.
7 | SpiceStar Academy ERP | Spice Academy | Satyam Prajapati | Manage student registration, screening test, medical details, fee management & academic sector record/ performance assessment for spicestar academy | - Reduce manual intervention of record creation. | UAT | Feb, 2018 | Feb, 2019 | NA | On Track | Not available
[5 empty] | - Process efficiency. |  | May, 2018
- Generating reports on basis of performance for the use of management.
8 | SOD & HOTAC for Crew (ARMS) | Travel Desk | Satyam Prajapati | - Integration with ARMS to achieve Crew movement and hotel alignment where Travel Desk Panel will receive hotel booking requests and allocate hotel accommodation (Contractual and Non-Contractual) for the crew. | - Operational Efficiency. | Requirement Analysis | NA | NA | TBD | Not Started
|  |  |  | - Billing and finance panel have been integrated for reporting purposes. | Travel history, approval over email and panel. | [5 empty] | NA
9 | SpiceJet Sister Concerns Booking | Travel Desk | Satyam Prajapati | SpiceJet Sister Concerns companies' Employee can request for Hotel as well as transport booking. Request has been approved by their respected HOD and finally hit on Travel desk for hotel alignment | This automation will overcome the manual hotel booking and approval. | Go Live | 2018-12-20 | 2019-02-13 | NA | On Track | NA
10 | NON-SOD Vendor Booking | Marketing, Reservations | Satyam Prajapati | NON-SOD Vendor booking (ITC, BFI etc )is part of SOD application. SOD System will provide right to User to book NON-SOD ticket. | This automation will overcome the manual vendors booking and approval. | Development | 2019-04-01 | TBD | TBD | Started | (I) Fixing testing issue (II) Working on vendor booking history
11 | SOD Bulk Booking-Phase 2 | Marketing,Reservations | Satyam Prajapati | Bulk/Group Booking alignment with Hotel booking/Multi Spoc booking and Alignment with Travel desk and Billing module/ Bulk Booking Partial Approval | This automation will overcome the manual bulk flight + hotel booking/only hotel booking for training staff. | Go Live | 2018-09-10 | 2019-03-30 | NA | On Track | Testing for Add new employee in existing list/Hotel cancellation from bulk booking history panel.
12 | SOD New Design/Enhancement | Reservations/Marketing/HR | Satyam Prajapati | A sustanable plate form where all the CR and various integrations, users ole will be manages dynamicaly and Admin having control | This new enhancement has overcome the various user role,right related issue and sustanable with apis and integrations. | Testing | Oct, 2018 | 15th-April | NA | On Track | New Project Testing & fixing the testing issue for go live..
13 | Spice Academy Performace Accessment | Spice Academy | Satyam Prajapati | Re-UI/UX design document | Enhancement in design as suggested by business | Document Design | 24/June,2019 | 2018-06-28 | NA | On Track | Completed - Design document/wireframe design- working on second phase for graphical data representation.
14 | Revisiting Distruption Module | Reservations | Satyam Prajapati | Passengers can choose an alternate flight or opt for full refund via Disruption Module in All IROP Scenarios.This option is available on SpiceJet website https://www.spicejet.com/ Under Change Flight or Refund. | Manage IROP scenario and Reduce the reservations call center load and manual intervention | Requirement Analysis | 11/July,2019 | NA | NA | Not Started | Worrking on design document to club the requirement and process flow.
15 | Travel Agent No Show amount Automation | Reservations | Satyam Prajapati | Travel Agency Login whereby they will be able to initiate a request for No-show refund against the PNR booked by them on their own once the booked passenger is declared No-Show for his/her flight. PNR will get auto-queued on NSHREV Queue (No Show Reversal Queue) | Automate the creation of No-Show Refund Queueing Option for Travel Agents - Automation of No-Show Refund | Requirement Analysis | 11/July,2019 | NA | NA | Not Started | Having discussion with business and working on design document to club the requirement and process flow.