## Peoject-List
SNO | Project Name | Line of Business | Project Manager (IT) | Description | Business Benefit | Project Phase | Project Start Date | Planned End Date | Revised End Date | Schedule RAG Status | Remarks
1 | ELT Booking | Reservations | Satyam Prajapati | Make the ELT process automated along with SSR included with PNR cancellation. | - Reduction of manual intervention in ELT bookings. | UAT | Oct, 2017 | 2018-02-21 | 2019-03-16 | Behind | - Project was put on hold initially due to Navitaire upgradation.
[5 empty] | - Process efficiency. |  | May, 2018 |  |  |  | - Phase 1 UAT is complete.
[5 empty] | - Visibility to user while booking under ELT | [5 empty] | - business is testing on the New UAT patch (including all changes)
- Awaiting a Go-ahead from Business to make the project live for all users.
- Project was behind because PNR cancellation (originally a part of Phase 2) was delivered in Phase 1 and dependant details API was not working as intended.
- Live credentials were requested by business to test Razorpay integration, this has been provided.
- Bugs have been reported by the reservations team related to the timings for international flights.Development team is working on fixing this bug.
2 | SOD OAT (Other Airline Ticketing) | Travel Desk | Satyam Prajapati | - Other Airline ticketing (OAT) module will capture Spicejet’s Employee Flight (NON-SpiceJet Airline) and Hotel booking requests (Contractual and Non-Contractual Hotel) | - Operational Efficiency | Development | Jan, 2018 | TBD | TBD | On Track | - The project went on hold due to other functional priorities on SOD Application.
[5 empty] | - This automation will overcome the manual hotel booking and approval. |  | March, 2018 |  |  |  | - Project was reinitiated in March, 2018 for few months and then again put on hold due to other functionalities.
[5 empty] | - Reduce system abuse. |  | March, 2019 |  |  |  | - This project is planned now and BRD creation is in process.
[5 empty] | - Notification of bookings will be automated. | [5 empty] | - Few New CR dependency and clearification is pending from business
3 | SOD ZOHO Expense Integrations | Finance, HR | Satyam Prajapati | Zoho Expense Integration with SOD application. | - Facilitate the employee to create trips on ZOHO Expense. | UAT | 2018-09-24 | 2019-03-29 | 2019-03-29 | On Track | - SOD integration with ZOHO Expense is complete as till requirement & waiting for feedback
[5 empty] | - Each trip created becomes a unique ID against which all non-CTC expenses are claimed, thus better view of all expenses for both Finance Team and the employee. |  |  |  | 2019-03-31 |  | - Testing is being currently performed on the functionality.
- Testing is pending with Finance due to ongoing HANA upgradation.
4 | SOD Feedback Level1 -Phase 1 | Marketing,SSQ | Satyam Prajapati | Provision to capture SOD feedback via SMS and reports for data analysis | Facilitate feedback collection from SOD travelers in a simple manner | Go Live | 2018-05-01 | 2018-12-05 | NA | On Track | User and Admin Panel with SMS , Navitaire integration
5 | SOD Feedback Level1 -Pahse 2 | Marketing,SSQ | Satyam Prajapati | Provision to capture SOD feedback via Email and reports for data analysis | Facilitate feedback collection from SOD travelers in a simple manner | Go Live | 2019-02-12 | 2019-03-10 | 2019-03-12 | On Track | - Project has completed
- Feedback submission orovision over Email/Email Notification
- Cross check submitted feedback via email
6 | SOD- Employee Change Request Management | Admin,HR | Satyam Prajapati | Provision to send request with HR/Finance Team for correction in personal information and changes in HOD | - Reduce manual intervention of sharing email ID and mobile no. before processing a booking. | Testing | 2018-09-24 | 2018-12-31 | 2019-04-30 | Behind | - Module has been integrated with new portal and changes have been updated on the UAT server.
[5 empty] | - Better user experience. | [5 empty] | - Bug fixing and UAT testing are going on
7 | SOD - Hotel Integration | Travel Desk | Satyam Prajapati | SOD/NON-SOD Booking automation for SpiceJet Employees/Vendors. | This automation will overcome the manual hotel booking and approval. | Go Live | 2016-03-01 | 2016-09-30 | 2018-12-31 | On Track | - Testing done on NON-Contractual Hotel Booking and functionalities.
[5 empty] | - Reduce misuse of the system. |  |  | 2018-12-31 |  |  | - Added functionalities to capture Travel desk Operator details.
[5 empty] | - Notification of bookings will be automated. | [5 empty] | -This project has been completed
8 | SOD-Spice Cab API Integration | Travel Desk | Satyam Prajapati | - Capture Spice cab data (training etc.) and push it to SOD- bulk booking module for processing flight & hotel bookings. | - Automation of travel desk will result in cost savings. | UAT | 2018-12-03 | 2019-04-30 | 2019-04-30 | On Track | API lisk has provided to business and waiting for feedback.Development work has closed as per requirement.
|  |  |  | - SOD application will provided an API to SpiceCab application, so that it can be integrated and push data from SpiceCab application to SOD database. | - ROI is high. |  |  | 2019-01-31
9 | SpiceStar Academy ERP | Spice Academy | Satyam Prajapati | Manage student registration, screening test, medical details, fee management & academic sector record/ performance assessment for spicestar academy | - Reduce manual intervention of record creation. | UAT | Feb, 2018 | Feb, 2019 | NA | On Track | SpiceStar cademy website's registration data integration process with ERP application.
[5 empty] | - Process efficiency. |  | May, 2018 |  |  |  | - Business has suggested a few CRs after testing the app.
[5 empty] | - Generating reports on basis of performance for the use of management. | [5 empty] | - Development team is working on these CRs.
10 | SOD & HOTAC for Crew (ARMS) | Travel Desk | Satyam Prajapati | - Integration with ARMS to achieve Crew movement and hotel alignment where Travel Desk Panel will receive hotel booking requests and allocate hotel accommodation (Contractual and Non-Contractual) for the crew. | - Operational Efficiency. | Requirement Analysis | NA | NA | TBD | Not Started | - Project is live.
|  |  |  | - Billing and finance panel have been integrated for reporting purposes. | Travel history, approval over email and panel. | [5 empty] | - CR is continuous in this project, presently the following developments are going on:
Bulk Booking COCKPIT/CREW Booking.
11 | SpiceJet Sister Concerns Booking | Travel Desk | Satyam Prajapati | SpiceJet Sister Concerns companies' Employee can request for Hotel as well as transport booking. Request has been approved by their respected HOD and finally hit on Travel desk for hotel alignment | This automation will overcome the manual hotel booking and approval. | Go Live | 2018-12-20 | 2019-02-13 | NA | On Track | This project is completed and live.
12 | SOD Bulk Booking-Phase 1 | Reservations | Satyam Prajapati | Bulk/Group Booking for Training, Ground Staff & Others departments. | This automation will overcome the manual flight booking/approvals | Go Live | 2016-08-19 | 2018-09-10 | NA | On Track | This project is completed and live.
13 | NON-SOD Vendor Booking | Marketing, Reservations | Satyam Prajapati | NON-SOD Vendor booking (ITC, BFI etc )is part of SOD application. SOD System will provide right to User to book NON-SOD ticket. | This automation will overcome the manual vendors booking and approval. | Not Yet Start | NA | NA | NA | Not Started | Not yet start.BRD has shared with business
14 | SOD Bulk Booking-Phase 2 | Marketing,Reservations | Satyam Prajapati | Bulk/Group Booking alignment with Hotel booking/Multi Spoc booking and Alignment with Travel desk and Billing module/ Bulk Booking Partial Approval | This automation will overcome the manual bulk flight + hotel booking/only hotel booking for training staff. | Go Live | 2018-09-10 | 2019-03-30 | NA | On Track | Major Enhancements Bulk booking alignment with Travel desk/Multi SPOC booking/Partial approval
15 | SOD New Design Enhancement | Reservations/Marketing/HR | Satyam Prajapati | A sustanable plate form where all the CR and various integrations, users ole will be manages dynamicaly and Admin having control | This new enhancement has overcome the various user role,right related issue and sustanable with apis and integrations. | Testing | Oct, 2018 | 15th-April | NA | On Track | This new enhancement has overcome the various users role/ rights related issue and sustanable with apis and integrations.